## Slide 1: prototype testing procedures and schedule
Dale E. Gary
Professor, Physics, Center for Solar-Terrestrial Research
New Jersey Institute of Technology

## Slide 2: outline
Initial Setup in Electronics Room
  Analog hardware assembly
  Correlator setup
  Computer control and communication
Initial Setup at Antenna
  Front end operation
  Antenna pointing (optical/radio)
  Feed focus
First Fringes
  Source tracking (satellite, Sun?)
  Receiving/recording data + plotting
  Spectral continuity, leveling
Array Configuration
  uvw coordinates, delay tracking, etc.
  Miriad interfacing
  Baseline determination
Schedule

## Slide 3: Initial setup in electronics room
Analog hardware assembly
  Kjell and Dan will assemble packages as they are completed and shipped (mid-Oct through Nov.)
  Cabling, basic interconnectivity, and power levels can be tested with test signals (e.g. Noise Diode, swept CW), by phone/email
Correlator setup
  After assembly at NJIT and basic testing, the correlator will be shipped to OVRO for integration (mid-November)
  Check clock, 1 pps, output of packets, operation via snap blocks (remotely via internet). Do we need LabVIEW test pgm?
Computer control and communication
  ACC control of analog hardware (test Modbus over RS-485 as soon as possible, so that final integration is possible remotely via internet)
  Schedule control of correlator (initiation, set delays)
  Sharing of state frame among computers

## Slide 4: Initial setup at antenna
Front end operation (December—Wes, Gelu, Dale on site)
  Hardware connections, verification of power levels.
  Develop and verify cRIO control/monitoring of front end
Antenna pointing (optical/radio)
  Optical pointing will be done early Oct, for initial pointing corrections (except zero-order offsets)
  Radio pointing requires peak-up (or drift scans) on Sun. Can we use raw 1-18 GHz power levels? RFI may limit => require end-to-end signal through correlator. When will DPP be ready—do we need a LabVIEW test program based on EST?
Feed focus
  The focus adjustment is manual—what is the procedure?
  Should be done at high frequency—what source? Is Sun okay?
  Isolating IF band requires end-to-end signal through correlator, possibly also DPP?

## Slide 5: First fringes (Requires DPP)
Source tracking (satellite, Sun?)
  Tracking the Sun will be needed for pointing anyway.
  Tracking on GPS, XM, etc., will need to be developed.
Receiving/recording data + plotting
  DPP will be needed for creating valid Miriad databases.
  Plotting can be done without Miriad itself (e.g. on Schedule computer via Aipy), or with Miriad by installing it on the Schedule computer => Pipeline computer not essential.
  Correct delays/fringe stopping are not needed, but it would be nice to demonstrate those and get stable phases.
Spectral continuity, leveling
  Test DPP operation for untangling spectra.
  Test correlator operation for leveling the bandpass.

## Slide 6: Array configuration
uvw coordinates, delay tracking, etc.
  Test generation of uvw coordinates and delays
  Seek to get flat phases without phase jumps in DPP output
Miriad interfacing
  Verify that Miriad scripts work
  Be able to create a working data file with averaging for calibration and science bands
Baseline determination
  Source? Test sensitivity on a calibrator (e.g. 3C84). May have to use satellites for rough first determination.
  Be able to set up a schedule for observing a calibrator list.
  Verify control of all subsystems for a complete observation.
  Create a valid baseline calibration file.
  Develop Miriad script for analyzing the baseline.

## Slide 7: schedule
2012 Oct-Nov:
  Dale & Gelu get ACC/cRIO control of antennas working + rudamentary schedule and stateframe.
  Wes sends hardware as it is completed to OVRO, where Kjell and Dan set it up with phone/email support.
  Toward end of period, correlator is shipped and set up with phone/email support.
2012 Early Dec:
  Wes, Dale & Gelu get front end installed and under control. Fix any problems with rest of system (may require Nimish).
  Initial attempt to determine feed best focus.
2012 Late Dec:
  Dale, Gelu, Nimish, Gordon, Jim set up DPP, attempt to get first fringes
2013 Jan.:
  Dale, Gelu, Nimish, Gordon, Jim, Stephen attempt to determine baseline corrections.
  Initial attempt to get calibrated data—evaluation of phase and amplitude stability