## Slide 1: prototype HARDware summmary
Dale E. Gary
Professor, Physics, Center for Solar-Terrestrial Research
New Jersey Institute of Technology

## Slide 2: schedule
2012 Oct 1-10: Dale & Gelu at OVRO
  get ACC/cRIO control of antennas working + rudamentary schedule and stateframe.
  get ROACH-1 remote boot and KATCP working
  optical pointing on the three prototype antennas
  get wet-dish brightness size/pattern
2012 Oct 15-Nov 15
  Kjell sets up racks in new building
  Wes sends timing subsystem for integration into rack, Kjell tests with phone/email support
  Correlator boards set up at NJIT, first testing of design begins
  Gelu tests RS-485 communication with Rabbit module
  DPP computer defined and ordered (shipped to OVRO)
  Dale writes EOVSA operations proposal!
2012 Nov 15-30:
  Wes completes assembly and test of LO subsystem and ships to OVRO for integration by Kjell/Stephen M.
  Nimish completes design and testing of correlator.
2012 Dec 1-15:
  Wes completes downconverter #1 & 2, ships to OVRO for integration by Kjell/Stephen M.
  Final decision to purchase long-lead items and enclosures—orders placed.
  Dale & Gelu at OVRO to develop control of LO and DC modules.
  Correlator shipped to OVRO, Nimish at OVRO to set up and do initial tests.
  Jim at OVRO to set up DPP computer.
2013 Jan 1-21
  Downconverter #3 and front-ends shipped to OVRO. Wes, Gelu, Dale at OVRO for control, integration/test.
  Jim, Gordon at OVRO for first operational test of DPP.
  Initial attempt to determine feed best focus, radio pointing, first fringes.

## Slide 3: Hardware issues
Analog system
Verify brightness spot size and design brightness sensor
Determine what temperature monitoring is needed in field (AUX box, controller), define and acquire hardware.
Determine what signal conditioning (inverting/duration of 1 pps, brightness sensor, FE trigger) is needed and design board for AUX box. May need analog, digital, and thermocouple modules?
Verify speed of RS-485 control of attenuators
Specify equalizer in DC (built into first DC amplifier)
Cryo-receivers
Find out lifetime # rating for Dow-key switches in 27-m front end.
Redo thermal budget calculation with latest design to ensure 77 K/15 K can be maintained for stage1/stage2.
Make final decisions re: couplers, amplifiers
Use 18 GHz low-pass filter from warm frontend
Correlator
Check implication of using 16-bit correlation data (throw away lowest 4 bits).
Check output of only two polarizations at a time vis a vis linear polarization calibration.

## Slide 4: prototype Software summmary
Dale E. Gary
Professor, Physics, Center for Solar-Terrestrial Research
New Jersey Institute of Technology

## Slide 5: Software issues
Control System
Complete the stateframe definition and distribute
Develop the scan-header implementation (things that are constant during a scan)
Schedule/Coordinate System
Check if linear interpolation of 1 s uvw is accurate enough
DPP
Verify that DPP can parse XML template and successfully read binary stateframe
Engineering Database
Define stateframe input, in order to permit database design
Investigate how to initialize “rich” static information
Investigate whether database can serve as fault system
Investigate whether database can drive display system through SQL queries
Metadata Database
Define keywords for FITS header, to use as metadata fields